## Gantt
[8 empty] | Baseline |  | Plan | [5 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27
# | Alert | Project / Version / Ticket | Key | Type | Assignee | Units | Priority | Status | Start | Finish | Start | Finish | Days | % Done | Due Date | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
1 |  | SharkSpotter2.0 |  | Project | [8 empty] | 0 | 0%
1-1 |  | Project Initiation | S0-1 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-08-14
1-1-1 |  | Define project scope and objectives | S0-2 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-13
1-1-2 |  | Define project deliverables | S0-4 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-13
1-1-3 |  | Identify project constraints | S0-5 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-14
1-2 |  | Stakeholder analysis | S0-6 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-08-10
1-2-1 |  | Identify stakeholders | S0-7 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-09
1-2-2 |  | Assess stakeholder interest and influence | S0-8 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-09
1-2-3 |  | Develop stakeholder management plan | S0-9 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-10
1-3 |  | Develop project charter | S0-10 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-08-14
1-3-1 |  | Define project purpose and objectives | S0-11 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-12
1-3-2 |  | Identify key project stakeholders | S0-12 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-13
1-3-3 |  | Outline project scope and constraints | S0-13 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-14
1-3-4 |  | Develop project timeline | S0-14 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-14
1-4 |  | Requirements Gathering | S0-15 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-08-28
1-4-1 |  | Conduct user interviews and surveys | S0-16 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-20
1-4-2 |  | Analyze user feedback | S0-17 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-23
1-4-3 |  | Document functional, usability, performance, security, and compliance requirements | S0-18 | Task |  | 100% | Medium | Done |  |  |  |  | 0 | 0% | 2023-08-28
1-5 |  | Design | S0-19 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-11
1-5-1 |  | Define system components and their interactions | S0-20 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-01
1-5-2 |  | Develop data flow diagrams | S0-21 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-03
1-5-3 |  | Develop system architecture diagrams | S0-22 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-06
1-5-4 |  | Select technologies and tools | S0-50 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-04
1-5-5 |  | Create wireframes and mockups for the GUI | S0-51 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-11
1-6 |  | Identify technology requirements | S0-24 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-7 |  | Evaluate available technologies and tools | S0-25 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-8 |  | Select appropriate technologies and tools | S0-26 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-9 |  | Create wireframes and mockups for the GUI | S0-27 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-10 |  | Development | S0-28 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-15
1-10-1 |  | Install necessary software and tools | S0-29 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-14
1-10-2 |  | Configure development environment | S0-30 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-15
1-10-3 |  | Test development environment setup | S0-31 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-16
1-10-4 |  | Define algorithm requirements | S0-32 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-18
1-10-5 |  | Use State of the Art algorithm | S0-33 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-24
1-10-6 |  | Test Model/Algorithm | S0-34 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-27
1-10-7 |  | Validate algorithm performance | S0-35 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-29
1-10-8 |  | Set up Wagtail and Django environment | S0-36 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-09-24
1-10-9 |  | Develop user interface components | S0-37 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-08
1-10-10 |  | Integrate user interface with object detection algorithm | S0-38 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-15
1-10-11 |  | Implement custom settings and feedback mechanism | S0-39 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-12
1-10-12 |  | Develop custom settings functionality | S0-40 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-15
1-10-13 |  | Test custom settings and feedback functionality | S0-41 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-15
1-11 |  | Testing | S0-42 | Epic |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-24
1-11-1 |  | Develop test cases | S0-43 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-19
1-11-2 |  | Conduct unit testing | S0-44 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-20
1-11-3 |  | Conduct integration testing | S0-45 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-22
1-11-4 |  | Conduct system testing | S0-46 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-23
1-11-5 |  | Validate functional requirements | S0-47 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-23
1-11-6 |  | Conduct usability testing | S0-48 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0% | 2023-10-24
1-11-7 |  | Test system performance and security | S0-49 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%
1-12 |  | SharkSpotter2.0 | S0-52 | Task |  | 100% | Medium | To Do |  |  |  |  | 0 | 0%